## Fixed Product Backlog
Sr. | Item | Requested by | Remarks
1 | Handling Bulk Non-FCR via Motive | CSE/CC | CEA: As per agreement with CC, the bulk complaint handler is under POC for Mobile. Once the solution is matured, we will implement similar solution for Fixed.
2 | Appointment by CCC for Dispatch Complaints (Technician Visit). | CSE | CEA: This is not pending with CEA, it’s under discussion with CC/CIT team as per attached email. Once all the stakeholders agree on the solution, CEA will assess the changes required in Motive and provide the project plan.
3 | Handling Closed SRs via Motive | CSE/Motive | It’s under implementation, ECD is 31st Dec 2018.
4 | Business Motive Enhancements.- Support Additional Voice VAS for Voice Products | CSE | Volume of the complaints need to be provided in order to assess the requirement.
5 | Business Motive Enhancements.- Enhance DEL (Product: VO) on IAD | CSE | Volume of the complaints need to be provided in order to assess the requirement.
6 | Business Motive Enhancements. -Voice VAS Rate Plan Inventory in Consumer & Business | CSE | The alignment will be commenced after the migration/upgrade to SMP7.
7 | Business Motive Enhancements. -DWC Accounts Troubleshooting | CSE | Volume of the complaints need to be provided in order to assess the requirement.
8 | Business Motive Enhancements. - Fixed LTE for Business in Business Motive | CSE | No details are provided in the shared document. Business team to provide more detailed requirement (including the volume) and the UC cases.
9 | Business Motive Enhancements. - MDU troubleshooting in Business Motive | CSE | No details are provided in the shared document. Business team to provide more detailed requirement (including the volume) and the UC cases.
10 | Business Motive Enhancements. -Bitstream Troubleshooting via Business Motive | CSE | No details are provided in the shared document. Business team to provide more detailed requirement (including the volume) and the UC cases.
11 | Handle the new CBCM account status | CEA
12 | IPTV STB Admin PIN : New policy -CSC Changes | CC | Waiting for Mgmt Approval
13 | IPTV STB Admin PIN : New policy -IVR Changes | CC
14 | Fixed 5G Commercial Product [158397] | BDDM
15 | Motive Fixed Provisioning. | CC | Waiting for CC feedback for the Motive WF
16 | <Non-Plc><154916><Fixed Number Portability (FNP)> | BDDM

## Scrum Backlog
Sr. | Item | Requested by | Tasks- Owner - Status | Sprint | Remarks
1 | Motive New unified WF | CEA
2 | IPTV STB Admin PIN : New policy -IVR Changes | CC
3 | FLTE enhancement.- BW Utilization | CTSC | Rehaab Kassim : Pending
4 | 154916 - Fixed Number Portability (FNP)-MR- BRD Business Bundles for FNP-Phase 2 | BDDM
5 | eNRM new API Requirements | CEA
6 | SSC for RvCPE | CEA | Rehaab Kassim : Development Completed
7 | IVR for password Reset | CCC | 1. Development of IVR- Internet Password reset. 2. Development of IVR-STB Admin Password reset. 3. Development of IVR-Wifi Password reset. 4. Development of IVR - Common WF for sending SMS.
8 | New Begin checks Development | CEA
9 | New IVR development | CEA
10 | New Predictive Development | CEA
11 | vIMS | FCP | 1. API testing. 2. DSA Development
12 | Game Stream | BDDM | 1. SA support for UAT. 2. Dev support of UAT. 3. Prod Deployment.
13 | Huawei new ONT HG8240H5 Testing | ND
14 | Fixed Business P1D3 and P3 CR | CSE/CC | 1. Design for the 8 pending JIRAs 2. Development for the 8 pending. 3. IQT testing for the completed 18 JIRAs. 4. Dev Support for the completed 18 JIRAs.
15 | UCaaS | MKT | 1. UCaaS- EvCPE development finalization. 2. UCaaS- Voice E2E testing. 3. UCaaS- EvCPE E2E testing. 4. UCaaS - IQT testing. 5. UCaaS - QA support for UAT. 6. UCaaS - SA Support for UAT. 7. UCaaS - Dev Support for UAT. 8. UCaaS - Prod Development. 9. EvCPE Development Completed(Rehaab Kassim)
16 | Motive Predictive ML Program | Mgmt
17 | Motive Predictive fault reduction Program | Mgmt
18 | Motive Predictive for Closed SR | ND
19 | SMP7 ATP | CEA
20 | Motive Script development | CEA
21 | COFs should be changed and “Error:” should be removed | Firas
22 | Motive - BigData - Fixed UDR integration
23 | Full Home Wi-Fi | MKT | Rehaab Kassim : Testing the requirement along with the ACS team.

## Sprint 23 Dec
Sr. | Scrum Members | Done | In Progress | To Do | Risk
1 | Basheer Faisal Abu Snainah | Motive Intelligent WF Design | 1. Gamestream UAT Support 2.ML Features Identification for CBCM & UPM 3. Fixed Technical Complaints Reduction | TBD
2 | Chandrika Sharma | Zhone 10G testing IVR Reset Internet Password WF IVR STB Reset Password WF | IVR Wifi Password Reset WF IVR Reset Internet Password testing
3 | Imthiyaz Ahamed Ali | 1.VIMS-ATS ,UDC wsdl tested 2.Fixed Phase 3 UAT Jira 3.P1 D3 Cr Iqt fix. | 1.Phase 3 UAT JIRA 2.Ucaas -CBCM,NRM and eNRM account availabity to E2E. 3.VIMS-DSA for ATS,UDC,ENS | 1.DSA for ATS-vIMS 2.Fixing Phase 3 UAT jira | 1.VIMS-User-call-admission value not available in ATS WSDL.(Sent mail to SA) 2.Waitning for Ucaas Account to troubleshoot E2E
4 | Prashob Mathummal Poyyeri | ONTDetailsScript,ACSBitStreamScript | ATP,AgamaQoEScript,SMP7 SSC Production setup | New Predictive Development(Workflow Changes), eNRM new API Requirements(DSA dev)
5 | Rehaab Kassim | SSC RvCPE | EvCPE | Full Home Wi-Fi
6 | Sarah Farukh | Huawei HG8240H5 ONT testing P1D3 CR IQT Support Zhone 10G Testing Phase 3 SIP Trunk UAT Phase 3 BIB UAT SMP7 IVR Adhoc support | Phase 3 SIP Trunk UAT support Phase 3 BIB UAT support Phase 3 SIP Trunk UAT Bug Resolve | Phase 3 BIB UAT support
7 | Simarpreet Singh | 1. Sandvine Dataset gathering with QoE details, 2. Motive Session Id code enhancement in Predictive. | 1. New Prediction development: Data collection from different BE and co-relation, for Machine Learning. 3. Closed SR Monitoring and Prediction redirection to SMP 7 | 1. New Prediction development: Co-relate Sandvine data with other BE details. 2. Prediction SMP 7 redirection. | Sandvine dataset is taking too long to load data. More than 2 hours etc.
8 | Sharma Saurabh
9 | Bondok Mohammed |  | 1.vIMS 2. ML Features Identification for VOIP feature 3. Fixed Technical Complaints Reduction | TBD
10 | Deepanshu Gupta | Consumer R08 Dataset Testing | Master Dataset Compilation | Dataset Analysis & Testing - Darwin
11 | Anne Neethu Thampy | P1D3 CR IQT Support Phase 3 SIP Trunk UAT Phase 3 BIB UAT | Huawei HG8240H5 ONT testing | UCaaS - IQT testing
12 | Somaya Tayseer Owais | Game Stream Development | Dev support of UAT Development of IVR - Common WF for sending SMS
13 | Priyanka Leo | Phase3 Development | Phase3 IQT Support | UCaaS

## Sprint 30 Dec
Sr. | Scrum Members | Done | In Progress | To Do
1 | Basheer Faisal Abu Snainah
2 | Chandrika Sharma
3 | Imthiyaz Ahamed Ali
4 | Prashob Mathummal Poyyeri
5 | Rehaab Kassim | 1. SSC-RvCPE 2. EvCPE for HIS | 1.Full Home Wi-Fi | 1.FLTE enhancement.- BW Utilization
6 | Sarah Farukh
7 | Simarpreet Singh
8 | Sharma Saurabh
9 | Bondok Mohammed
10 | Deepanshu Gupta
11 | Anne Neethu Thampy
12 | Somaya Tayseer Owais
13 | Priyanka Leo | Phase3 IQT Support | Phase 3 & P1D3 UAT Support | COFs should be changed and “Error:” should be removed